## Sheet1
|  | Project Plan |  |  | Total No. of Days Left
|  | Days (Date Range) | Tasks |  | 24
|  | 3 (15 till 17) | Author Functions
|  | 2 (18 till 19) | Reviewer Functions
|  | 5 (20 till 24) | Chair Functions
|  | 5 (25 till 29) | Integration
|  | 2 (30 and 31) | Buffer
|  | 5 (01 till 05) | Testing
|  | 2 (06 and 07) | Documentation
|  | 8th | SUBMISSION
Sl No. | Tasks | Front End | Fadi | Prasad | Shashi | Date | Back End | Yasin | Ahmad | Date
1.0.0 | Responsive design
2.0.0 | User Functions
2.1.0 | Register to the system at least with email, password(emails are unique)
2.1.1 | Users can have multiple roles (e.g., author and reviewer)
2.1.2 | Basic profile (given name, family name, postal address)
2.1.3 | Affiliation (institution, city, state, country)
2.2.0 | login to the system at least with registered email, password
2.3.0 | edit my profile (password, additional information) |  |  |  | *** | 19.08.2016
2.4.0 | remove my profile
2.5.0 | logout
3.0.0 | Author Functions
3.1.0 | create a new submission (if submission is open)
3.1.1 | title
3.1.2 | registered authors [1..*] (given name, family name, email affiliation)
3.1.3 | abstract
3.1.4 | keywords (multi-selection) that describe the submission (e.g., research fields)
3.1.5 | upload the paper (.pdf)
3.2.0 | access current submissions (overview) |  |  |  | *** | 16.08.2016
3.2.1 | status: incompleted, completed, closed, accepted, rejected
3.3.0 | look at a submission
3.4.0 | edit a submission (if submission is open) |  |  |  | *** | 17.08.2016
3.5.0 | withdraw a submission
4.0.0 | Reviewer Functions
4.1.0 | access assigned submissions (overview + status)
4.2.0 | look at an assigned submission
4.2.1 | details, pdf download or view
4.3.0 | make a review > template (if review is open) |  |  |  | *** | 21.08.2016
4.3.1 | reviewer expertise: (1) not familar w/ the topic - (5) expert |  |  |  | *** | 21.08.2016
4.3.2 | overall evaluation: (1) strong reject - (5) strong accept |  |  |  | *** | 21.08.2016
4.3.3 | summary |  |  |  | *** | 21.08.2016
4.3.4 | major strong popints |  |  |  | *** | 21.08.2016
4.3.5 | major weak points |  |  |  | *** | 21.08.2016
4.3.6 | detailed comments |  |  |  | *** | 21.08.2016
4.4.0 | edit a review (if reviewing phase is open) |  |  |  | *** | 21.08.2016
5.0.0 | Chair Functions
5.1.0 | list all paper submissions |  |  | *** |  | 19.08.2016
5.1.1 | look at a submissions (details, pdf download or view) |  |  | *** |  | 19.08.2016
5.1.2 | withdraw a submission |  |  | *** |  | 19.08.2016
5.2.0 | list all authors |  |  | *** |  | 19.08.2016
5.2.1 | look at detail information |  |  | *** |  | 19.08.2016
5.3.0 | list all reviewers |  |  | *** |  | 19.08.2016
5.3.1 | look at detail information |  |  | *** |  | 19.08.2016
5.4.0 | list all reviews |  |  | *** |  | 19.08.2016
5.4.1 | look at a review |  |  | *** |  | 19.08.2016
5.5.0 | assign papers to reviewers |  |  | *** |  | 21.08.2016
5.5.1 | conflict avoidance: an author is not allow to review his own paper |  |  | *** |  | 21.08.2016
5.6.0 | do the schedule management |  |  | *** |  | 21.08.2016
5.6.1 | automatic: set close deadlines for submissions and reviews |  |  | *** |  | 21.08.2016
5.6.2 | manual: (re-)open/close submissions and reviews |  |  | *** |  | 21.08.2016
| create new conference |  |  | *** |  | 21.08.2016
| invit authot to conference |  |  | *** |  | 21.08.2016
| edit conference info |  |  | *** |  | 21.08.2016
5.7.0 | view fancy summary charts or reports (e.g., total submission, acceptances, topics, countries etc.)
6.0.0 | Bonus features (OPTIONAL)
6.0.1 | users must confirm their registration by clicking on a registration link sent via email
6.0.2 | email notification to submitters and reviewers (status changes)
6.0.3 | chat with other online authors
6.0.4 | automatic assignment (even distribution) and conflict resolving
6.0.5 | [NEW] a user can create multiple conference events and becomes the chair (=administrator) of them